## Read me
Shell data platform – access requests for the new DevOps process
Repo: <shell-org>/shell-data-platform · GitHub Actions · Azure Boards · ADF · Databricks Asset Bundles · Azure SQL config DB · Requested by Vamshi Singam
How to use
1. 'Access requests' has one row per permission. Columns M–P (yellow) are for the admin: set Status, your name, date, comments.
2. Filter column C ('Granted by') to see only the rows your team owns.
3. Phase P1 rows block the start of development; P2 rows are needed before the first QA release; P3 before the first PROD release.
4. 'Names to return' lists the resource names and IDs we need back (yellow cells).
5. 'Open questions' must be answered first: several rows depend on them (see Notes column).
No passwords or secrets are requested for Azure: GitHub signs in with the existing managed identities through federated credentials.
Summary by owner
Granted by | Total | P1 rows | Granted | Open
GitHub org owner | 12 | 9 | 0 | 12
Entra ID admin / identity owner | 6 | 4 | 0 | 6
Azure subscription owner (RBAC) | 8 | 7 | 0 | 8
Azure SQL server Entra admin | 4 | 4 | 0 | 4
Databricks account admin | 1 | 1 | 0 | 1
Databricks workspace admin / UC catalog owner | 8 | 7 | 0 | 8
Azure DevOps (Boards) project admin | 2 | 1 | 0 | 2
ServiceNow platform admin | 2 | 0 | 0 | 2
Network / cloud platform team | 2 | 1 | 0 | 2
Existing data/DevOps team (information) | 2 | 1 | 0 | 2
Total | 47 | 35 | 0 | 47
Phases
P1: Start building: DEV, feature-branch testing, PR checks
P2: First release to QA and UAT
P3: First release to PROD
Legend: ● = applies to that environment · yellow cells = for the admin to fill in

## Access requests
ID | Area | Granted by | Principal / target | DEV | QA | UAT | PROD | Permission / action requested | Why it is needed | Phase | Notes | Status | Granted by (name) | Date | Admin comments
GH-01 | GitHub | GitHub org owner | Vamshi Singam (lead) |  |  |  |  | Create private/internal repo <shell-org>/shell-data-platform; give the lead Admin role on it during setup | New parallel process needs its own repo with ADF, Databricks and SQL projects side by side | P1 |  | Requested
GH-02 | GitHub | GitHub org owner | GitHub teams: developers, tech-leads, release-managers, qa-leads, uat-signoff |  |  |  |  | Create or map teams (ideally synced from Entra groups); repo roles: developers = Write, tech-leads = Maintain, release-managers = Maintain | Drives CODEOWNERS review and environment approvers | P1 |  | Requested
GH-03 | GitHub | GitHub org owner | Repo settings |  |  |  |  | Allow squash merge only (disable merge commits and rebase merge); auto-delete head branches | One PR = one commit on main, which makes releases selectable by PR number | P1 |  | Requested
GH-04 | GitHub | GitHub org owner | Ruleset on main |  |  |  |  | Require PR; 1 approval from CODEOWNERS (tech-leads); dismiss stale approvals; require status check 'pr-validation'; require conversation resolution; block force-push and deletion; no bypass except org admins | Gate 1: only reviewed, tested PRs reach main | P1 |  | Requested
GH-05 | GitHub | GitHub org owner | Ruleset on release/* branches and prod/* tags |  |  |  |  | Restrict create/update/delete; bypass list = release-bot GitHub App only | Nobody hand-edits a release branch or moves a production tag | P2 |  | Requested
GH-06 | GitHub | GitHub org owner | GitHub App 'shell-data-release-bot' |  |  |  |  | Create app (Contents: read & write, Pull requests: read, Metadata: read), install on the repo only; give its App ID and private key to the lead for the 'release-cut' environment secret | Cuts release/<id> branches and pushes prod/<id> tags past the ruleset in GH-05 | P2 |  | Requested
GH-07 | GitHub | GitHub org owner | GitHub Actions policy |  |  |  |  | Enable Actions on the repo; allow actions: actions/*, azure/login, databricks/setup-cli, Azure/arm-deploy, Azure/sql-action (or allow 'verified creators') | Workflows for validation, feature environments and releases | P1 |  | Requested
GH-08 | GitHub | GitHub org owner | Workflow permissions / OIDC |  |  |  |  | Default GITHUB_TOKEN = read; workflows may request id-token: write (OIDC). Confirm no org policy blocks OIDC | Passwordless sign-in to Azure with the existing managed identities | P1 |  | Requested
GH-09 | GitHub | GitHub org owner | GitHub Environments | ● | ● | ● | ● | Create environments: dev-feature, dev, release-cut, qa, uat, prod. Required reviewers: qa = qa-leads, uat = uat-signoff, prod = release-managers. Deployment branches: dev-feature = feature/**, bugfix/**; dev = main; release-cut = main; qa/uat/prod = release/* | Gates 3, 4 and 6 are environment approvals | P1 | Required reviewers on a private/internal repo need GitHub Enterprise (confirm plan, see OQ-07) | Requested
GH-10 | GitHub | GitHub org owner | Environment secrets |  |  | ● | ● | Store ServiceNow integration credentials as secrets in the 'prod' environment only (and 'uat' if the CR is checked before UAT) | Gate 5 reads and updates the change request | P3 |  | Requested
GH-11 | GitHub | GitHub org owner | Third-party app access | ● |  |  |  | Approve the 'Azure Data Factory' and 'Databricks' GitHub apps / OAuth apps for the org (if OAuth app access restrictions are on) | DEV factory Git mode and Databricks Git folders must read feature branches: this is what makes feature-branch testing possible | P1 | Blocking for feature testing | Requested
GH-12 | GitHub | GitHub org owner | GitHub Actions runners | ● | ● | ● | ● | GitHub-hosted runners if Azure endpoints are public. If ADF/SQL/Databricks are private: self-hosted runners in a VNet with line of sight (or GitHub-hosted runners with Azure private networking), registered to this repo | Runners must reach SQL (DACPAC), Databricks and ARM endpoints | P1 | Depends on OQ-03 | Requested
ID-01 | Identity | Entra ID admin / identity owner | Existing managed identities | ● | ● | ● | ● | Confirm each identity we reuse is USER-assigned and give: name, client ID, object ID, resource group, tenant ID | GitHub can only sign in through a user-assigned identity (or app registration); system-assigned identities (for example the factory's own) cannot take federated credentials | P1 | If they are system-assigned, request one user-assigned identity per environment instead (see OQ-04) | Requested
ID-02 | Identity | Entra ID admin / identity owner | Deploy identity – DEV | ● |  |  |  | Add federated credentials: issuer https://token.actions.githubusercontent.com, audience api://AzureADTokenExchange, subjects repo:<shell-org>/shell-data-platform:environment:dev and …:environment:dev-feature | deploy-dev and feature-env workflows | P1 | Needs Contributor/Owner on the identity to add | Requested
ID-03 | Identity | Entra ID admin / identity owner | CI identity (read-only) – DEV | ● |  |  |  | Federated credential subject repo:<shell-org>/shell-data-platform:pull_request (a separate low-privilege identity is preferred; DEV deploy identity acceptable) | pr-validation runs ADF validate and bundle validate against DEV | P1 |  | Requested
ID-04 | Identity | Entra ID admin / identity owner | Deploy identity – QA, UAT |  | ● | ● |  | Federated credentials with subjects …:environment:qa and …:environment:uat (on each environment's identity) | release workflow QA and UAT jobs | P2 |  | Requested
ID-05 | Identity | Entra ID admin / identity owner | Deploy identity – PROD |  |  |  | ● | Federated credential with subject …:environment:prod | release workflow PROD job (runs only after release-manager approval) | P3 |  | Requested
ID-06 | Identity | Entra ID admin / identity owner | Entra security groups |  |  |  |  | Create or confirm groups: grp-data-developers, grp-data-techleads, grp-data-qa, grp-data-uat-signoff, grp-data-release-managers | Used for Azure RBAC, SQL, Databricks and GitHub team sync | P1 |  | Requested
AZ-01 | Azure RBAC | Azure subscription owner (RBAC) | Deploy identity – each env | ● | ● | ● | ● | Data Factory Contributor on the resource group that holds that environment's factory | ARM template deployment, stop/start triggers, delete removed pipelines | P1 DEV · P2 QA/UAT · P3 PROD |  | Requested
AZ-02 | Azure RBAC | Azure subscription owner (RBAC) | Deploy identity – DEV | ● |  |  |  | SQL DB Contributor on the DEV SQL logical server | Create, copy and drop feature databases sqldb-etlcfg-ft-<story> | P1 | DEV only | Requested
AZ-03 | Azure RBAC | Azure subscription owner (RBAC) | DEV SQL logical server | ● |  |  |  | Create elastic pool 'pool-etlcfg-feature' (small, e.g. GP 2 vCore or 50–100 eDTU) on the DEV server; name a cost owner | Feature databases share one capped pool; nightly cleanup keeps it small | P1 | Sizing/cost decision (OQ-05) | Requested
AZ-04 | Azure RBAC | Azure subscription owner (RBAC) | Deploy identity – each env | ● | ● | ● | ● | Reader on the environment's data-platform resource group(s) | Look up resource IDs, run ARM what-if | P1 DEV · P2 QA/UAT · P3 PROD |  | Requested
AZ-05 | Azure RBAC | Azure subscription owner (RBAC) | grp-data-developers | ● |  |  |  | Data Factory Contributor on the DEV factory only | Author in Git mode and debug pipelines on feature branches | P1 | No write access to QA/UAT/PROD factories | Requested
AZ-06 | Azure RBAC | Azure subscription owner (RBAC) | grp-data-developers |  | ● | ● | ● | Reader (or Data Factory monitoring via Reader) on QA/UAT/PROD factories | Monitor runs without changing anything | P2 |  | Requested
AZ-07 | Azure RBAC | Azure subscription owner (RBAC) | Factory managed identity (existing) – each env | ● | ● | ● | ● | Verify existing: Storage Blob Data Contributor on ADLS; Key Vault Secrets User on the Key Vault used by linked services | Pipelines keep working after deployments | P1 | Verification only | Requested
SQL-01 | Azure SQL | Azure SQL server Entra admin | Each config SQL logical server | ● | ● | ● | ● | Confirm Microsoft Entra admin is set and Entra authentication is enabled; give server and database names | Identities sign in without passwords | P1 |  | Requested
SQL-02 | Azure SQL | Azure SQL server Entra admin | Deploy identity – each env | ● | ● | ● | ● | In the config DB: CREATE USER [<deploy-identity>] FROM EXTERNAL PROVIDER; ALTER ROLE db_owner ADD MEMBER [<deploy-identity>] | DACPAC deploys schema, permissions and config rows | P1 DEV · P2 QA/UAT · P3 PROD | In DEV this user is copied into every feature DB automatically | Requested
SQL-03 | Azure SQL | Azure SQL server Entra admin | Factory managed identity (existing) – each env | ● | ● | ● | ● | Verify it is a user in the config DB with db_datareader, db_datawriter and EXECUTE | ADF reads config and writes watermarks; copied into feature DBs automatically | P1 | Verification only | Requested
SQL-04 | Azure SQL | Azure SQL server Entra admin | grp-data-developers | ● |  |  |  | db_datareader on sqldb-etlcfg-dev | Inspect config; the feature-env workflow grants write access on each feature DB itself | P1 |  | Requested
SQL-05 | Azure SQL | Network / cloud platform team | Config SQL servers – network | ● | ● | ● | ● | Allow the runners from GH-12 to reach port 1433: private endpoint + VNet runners, or firewall rule for static runner IPs | DACPAC deployment and feature-DB setup | P1 | Depends on OQ-03 | Requested
DBX-01 | Databricks | Databricks account admin | Deploy identity – each env | ● | ● | ● | ● | Add the identity (by client ID) as a service principal in the Databricks account; assign it to that environment's workspace with 'Workspace access' | Databricks CLI deploys asset bundles as this identity | P1 DEV · P2 QA/UAT · P3 PROD |  | Requested
DBX-02 | Databricks | Databricks workspace admin / UC catalog owner | Deploy identity – each env | ● | ● | ● | ● | CAN MANAGE on the bundle root folder (e.g. /Workspace/Shared/shell-data); allowed to create jobs | bundle deploy creates and updates jobs, notebooks and pipelines | P1 DEV · P2 QA/UAT · P3 PROD |  | Requested
DBX-03 | Databricks | Databricks workspace admin / UC catalog owner | Deploy identity – each env | ● | ● | ● | ● | CAN USE on the job cluster policy, or serverless jobs enabled | Jobs defined in the bundle can start compute | P1 DEV · P2 QA/UAT · P3 PROD | Depends on OQ-02 | Requested
DBX-04 | Databricks | Databricks workspace admin / UC catalog owner | Deploy identity – each env | ● | ● | ● | ● | If jobs run as an existing run-as service principal: 'Service Principal: User' role on that principal | Bundle sets run_as on production jobs | P2 |  | Requested
DBX-05 | Databricks | Databricks workspace admin / UC catalog owner | Deploy identity – each env | ● | ● | ● | ● | Unity Catalog on the environment catalog: USE CATALOG, USE SCHEMA, CREATE SCHEMA, CREATE TABLE, CREATE FUNCTION, CREATE VOLUME, MODIFY, SELECT (or ownership of bundle-managed schemas) | Bundle-managed DDL and grants | P1 DEV · P2 QA/UAT · P3 PROD |  | Requested
DBX-06 | Databricks | Databricks workspace admin / UC catalog owner | Deploy identity – each env | ● | ● | ● | ● | CAN USE on one SQL warehouse | Run UC SQL steps during deployment | P1 DEV · P2 QA/UAT · P3 PROD |  | Requested
DBX-07 | Databricks | Databricks workspace admin / UC catalog owner | Factory managed identity (existing) – each env | ● | ● | ● | ● | Verify it is a workspace service principal; give its client ID so the bundle grants it CAN MANAGE RUN on the jobs it triggers | ADF triggers Databricks jobs after every deployment | P1 | Verification + information | Requested
DBX-08 | Databricks | Databricks workspace admin / UC catalog owner | grp-data-developers | ● |  |  |  | DEV workspace access; serverless/cluster use; on dev catalog: USE CATALOG, CREATE SCHEMA (personal dev_<user> schemas) | Developers deploy bundles in development mode: resources prefixed with their name, isolated per developer | P1 |  | Requested
DBX-09 | Databricks | Databricks workspace admin / UC catalog owner | DEV workspace – Git integration | ● |  |  |  | Allow Git folders to the GitHub org (add repo to the Git allowlist if restricted) | Developers work on feature branches inside the workspace | P1 |  | Requested
ADF-01 | ADF | Azure subscription owner (RBAC) | DEV factory | ● |  |  |  | Connect the DEV factory to GitHub: repo shell-data-platform, collaboration branch main, root folder /adf; turn ON 'Disable publish' (automated publish) | Feature branches can be debugged; main is deployed by the pipeline, not the Publish button | P1 | Done by the lead once AZ-05 and GH-11 are granted | Requested
ADF-02 | ADF | Existing data/DevOps team (information) | Integration runtimes | ● | ● | ● | ● | Names/types of integration runtimes (Azure, self-hosted, shared/linked) used by each factory | ARM parameter files map linked services to the right runtime per environment | P1 | Information | Requested
ADO-01 | Azure Boards | Azure DevOps (Boards) project admin | Azure Boards app |  |  |  |  | Install the Azure Boards app on the GitHub org and connect the ADO project to shell-data-platform (needs ADO project admin + GitHub org owner) | AB#1234 in a PR links it to the story; PR check blocks merges without a story | P1 |  | Requested
ADO-02 | Azure Boards | Azure DevOps (Boards) project admin | Deploy identity (QA/UAT/PROD, or one release identity) |  | ● | ● | ● | Add the managed identity to the Azure DevOps organization (Basic access); Contributor on the project or area path | Release workflow moves stories to Ready for QA / Ready for UAT / Closed and comments the release id | P2 |  | Requested
ADO-03 | Azure Boards | Existing data/DevOps team (information) | Board process |  |  |  |  | Confirm work-item state names and the area path used by this team | Workflow uses the exact state names | P2 | Information | Requested
SN-01 | ServiceNow | ServiceNow platform admin | Integration account / OAuth client |  |  |  | ● | Integration user (or OAuth client credentials) able to read change_request and update state and work_notes for this team's assignment group | Gate 5: CR approved + in window + PR list matches; evidence written back after deploy | P3 |  | Requested
SN-02 | ServiceNow | ServiceNow platform admin | Change template |  |  |  | ● | Add a field (e.g. u_release_prs) or agree the description lines 'Release-Id:' and 'Release-PRs:' on the CR template; confirm change model (Normal/Standard) | Ties each CR to the exact PRs being deployed | P3 |  | Requested
SN-03 | ServiceNow | Network / cloud platform team | ServiceNow instance – network |  |  |  | ● | If the instance restricts inbound IPs, allow the runner egress IPs | Runners call the ServiceNow Table API | P3 | Conditional | Requested

## Names to return
Item | DEV | QA | UAT | PROD
Tenant ID
Subscription ID
Resource group (data platform)
Deploy identity name (user-assigned)
Deploy identity client ID
Data Factory name | adf-…-dev
Factory managed identity client ID
SQL logical server
Config database | sqldb-etlcfg-dev
Databricks workspace URL | https://adb-….azuredatabricks.net
Unity Catalog catalog
SQL warehouse ID
Self-hosted IR name (if any)
Key Vault name
Grey italic values in the DEV column are examples of the expected format; overwrite them.

## Open questions
ID | Question | What it affects | Who can answer | Answer
OQ-01 | Is each environment (DEV, QA, UAT, PROD) in its own subscription? Resource group and resource names per env? | Scopes for every Azure role assignment | Vamshi / platform team
OQ-02 | Is Databricks serverless (jobs and SQL) allowed, or must jobs use a cluster policy? | DBX-03 and bundle job definitions | Databricks admin
OQ-03 | Are ADF, Azure SQL and Databricks behind private endpoints? Which self-hosted integration runtimes exist? | Runner choice (GH-12), SQL-05, ADF-02 | Network team
OQ-04 | Are the managed identities we must reuse user-assigned or system-assigned? | If system-assigned, GitHub cannot use them: new user-assigned identities are needed | Entra admin
OQ-05 | Elastic pool size and cost owner for feature databases | AZ-03 | Budget owner
OQ-06 | How are Azure SQL scripts deployed today (SQL project/DACPAC, numbered scripts, other)? | Decides the SQL project tooling; process stays the same | Existing team
OQ-07 | Which GitHub plan does the org have (Enterprise Cloud?) | Environment required reviewers on private/internal repos need GitHub Enterprise | GitHub org owner
OQ-08 | ServiceNow: assignment group, change model, and whether CRs can be read/updated via API | SN-01, SN-02 | ServiceNow admin